## EB2-NIW
| STATUS | Not Started | In Progress | Complete | On Hold | Overdue | Needs Review |  | Canceled |  |  | Payment
MONTHLY PRODUCT RELEASE GANTT CHART | [7 empty] | 2024 | [7 empty] | 2025 | [11 empty] | 2026
[8 empty] | Q2 |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4 |  |  | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
ID | ACTIVITY | STATUS | OWNER | DEPENDENCIES | START DATE | END DATE | DURATION | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
1 | CONTRATO E PAGAMENTO |  |  |  | 2024-05-29 | 2024-06-07 | 8
1A | Reunião Orlando | Complete | Bicalho + Giovanna |  | 2024-05-29 | 2024-05-29 | 1
1B | Envio Contrato | Complete | Bicalho |  | 2024-05-31 | 2024-05-31 | 1
1C | Assinatura Contrato | In Progress | Giovanna/Fabio |  | 2024-06-01 | 2024-06-07 | 5
1D | Pagamento 1/10 [$1,900] | Not Started | Giovanna |  | 2024-06-26 | 2024-06-26 | 1
2 | CONSTRUÇÃO DO CASO |  |  |  | 2024-06-12 | 2024-10-01 | 80
2A | Kick-off Meeting | Not Started | Bicalho + Giovanna | 1C | 2024-06-12 | 2024-06-12 | 1
2B | Enviar Documentos (1m) | Not Started | Giovanna | 2A | 2024-06-13 | 2024-07-31 | 35
2C | Construção do Caso (3m-6m) | Not Started | Bicalho | 2B | 2025-06-25 | 2025-09-20 | 63
2D | Expert Opinion Letter ($1,000) | Not Started
Not Started
2D | Taxa Imigratória ($1,015) | Not Started |  |  | 2025-07-21 | 2025-11-05 | 78
3 | AVALIAÇÃO USCIS |  |  |  | 2024-10-01 | 2025-11-30 | 304
3A | Resposta (10m-14m) | Not Started |  |  | 2025-04-12 | 2025-07-13 | 65
3B | AOS (Ajuste de Status) ($2,500) | Not Started |  |  | 2025-05-23 | 2025-09-27 | 91
3C | Combo Card (Nov 25 - Jun 26) | Not Started |  |  | 2025-08-15 | 2025-11-12 | 64
3D | Release 4 | Not Started |  |  | 2025-09-08 | 2025-11-30 | 60
4 | NVC & ENTREVISTA |  |  |  | 2025-06-01 | 2025-12-22 | 146
4A | Release 1 | Not Started |  | 1A, 2A | 2025-06-01 | 2025-07-29 | 42
4B | Release 2 | Not Started |  |  | 2025-07-08 | 2025-11-14 | 94
4C | Release 3 | Not Started |  |  | 2025-09-20 | 2025-11-14 | 40
4D | Release 4 | Not Started |  |  | 2025-09-22 | 2025-12-22 | 66
Formulas:
Needs Review = NETWORKDAYS([On Hold],[Overdue])

## Template
STATUS | Not Started | In Progress | Complete | On Hold | Overdue | Needs Review | Canceled
MONTHLY PRODUCT RELEASE GANTT CHART
[8 empty] | Q1 |  |  | Q2 |  |  | Q3 |  |  | Q4
ID | PORTFOLIO | STATUS | OWNER | DEPENDENCIES | START DATE | END DATE | DURATION | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
1 | PRODUCT ID |  |  |  | 2025-01-20 | 2025-09-27 | 180
1A | Release 1 | Complete |  |  | 2025-01-20 | 2025-04-12 | 60
1B | Release 2 | In Progress |  |  | 2025-02-25 | 2025-06-30 | 90
1C | Release 3 | On Hold |  |  | 2025-05-15 | 2025-08-11 | 63
1D | Release 4 | Needs Review |  |  | 2025-06-15 | 2025-09-27 | 75
2 | PRODUCT ID |  |  |  | 2025-02-25 | 2025-11-05 | 182
2A | Release 1 | Overdue |  | 1A | 2025-02-25 | 2025-05-20 | 61
2B | Release 2 | Not Started |  |  | 2025-04-01 | 2025-08-03 | 89
2C | Release 3 | Not Started |  |  | 2025-06-25 | 2025-09-20 | 63
2D | Release 4 | Not Started |  |  | 2025-07-21 | 2025-11-05 | 78
3 | PRODUCT ID |  |  |  | 2025-04-12 | 2025-11-30 | 165
3A | Release 1 |  |  | 1D | 2025-04-12 | 2025-07-13 | 65
3B | Release 2 |  |  |  | 2025-05-23 | 2025-09-27 | 91
3C | Release 3 |  |  |  | 2025-08-15 | 2025-11-12 | 64
3D | Release 4 |  |  |  | 2025-09-08 | 2025-11-30 | 60
4 | PRODUCT ID |  |  |  | 2025-06-01 | 2025-12-22 | 146
4A | Release 1 |  |  | 1A, 2A | 2025-06-01 | 2025-07-29 | 42
4B | Release 2 |  |  |  | 2025-07-08 | 2025-11-14 | 94
4C | Release 3 |  |  |  | 2025-09-20 | 2025-11-14 | 40
4D | Release 4 |  |  |  | 2025-09-22 | 2025-12-22 | 66
Formulas:
Canceled = NETWORKDAYS([Overdue],[Needs Review])